Colorado Traumatic Brain Injury Program

Board Meeting Minutes

Date: 	3/6/17	 						Time: 10:30-11:30 A.M.

| TYPE OF MEETING | Research and Program Evaluation Committee meeting |
| --- | --- |
| FACILITATOR | Helen Morgan, Board Chair and Judy Dettmer, Program Director |
| ATTENDEES |
| NAME | POSITION | PRESENT | STAFF Present |
| (Members) |  |  |  |
| Catie Johnston-Brooks | Committee Chair |  | Judy Dettmer |
| Terry Chase | Committee Member |  |  |
| Indira Gujral | Committee Member |  |  |
| Pat Schniederjan | Committee Member |  |  |

1.  Agenda topic:  Letter of Intent

| Discussion | Discussed the pros and cons of having a letter of Intent (LoI) Pros gives us a heads up in terms of who solicit for reviewers Helps guide the researcher as to which type of science they might want to apply for Helps researcher flesh out their research idea Cons In the past the procurement officer has indicated that we cannot require this unless we want to score the LoI |
| --- | --- |
| Action Items | Person(s) Responsible | Deadline |
| Judy will check with procurement to see if it would be required to score the LoI if we include this. Committee will make a final decision on inclusion of LoI prior to next RFP | Judy Committee | July 1, 2017 October 2017 |

2.  Agenda topic:  Pros and Cons of Separate RFPs

| Discussion | As this was the first funding cycle where there was a distinct RFP for each type of research, the committee discussed if that is something we would like to continue. Committee felt having separate RFPs is helpful due to the difference between basic science, new investigator, and clinical Judy gave feedback that it appeared that people had a hard time knowing if their proposal would fit under clinical or health outcomes. Committee felt those two types of research could be combined under the same RFP |
| --- | --- |
| Action Items | Person(s) Responsible | Deadline |
| The Program will combine Clinical and Health Outcomes research under one RFP next funding cycle. | Judy | Next RFP cycle |

3.  Agenda topic:  Re-evaluate New Investigator Category

| Discussion | This year was the first year for the New Investigator award category. We did not receive any applications under this category. The committee discussed ways to improve this in the future. Decided more targeted outreach needed to occur to Universities and new hospital faculty. Need to revisit the announcement and review eligibility criteria etc. to ensure we are more effectively targeting new investigators. Explore the idea of advisor or mentor for new investigators. |
| --- | --- |
| Action Items | Person(s) Responsible | Deadline |
| Committee will take a careful look at this RFP prior to the next funding cycle | Committee | Oct. 2017 |

5.  Agenda topic:  Promotion of Research Grant Program

| Discussion | Overall the committee felt we could have a stronger effort to promote the awareness of these funding opportunities. Some initial ideas include sending out call for posters to current and past researchers for the Craig Hospital Brain Injury Summit and other relevant conferences. Promoting grants within various professional organizations Put out on various web notifications and list serves that researchers are connected to Build a comprehensive data base |
| --- | --- |
| Action Items | Person(s) Responsible | Deadline |
| Continue to discuss and flesh this out prior to next funding cycle. Send call for poster notification to current and past researchers for Craig Hospital conference. | Committee CBIP Staff | Prior to next RFP Cycle May 2017 |